## Slide 1: AILA CRM: infrastructure costing and delivery plan
Monolithic .NET 10 + Angular application on one Azure server
Notes: Ready-to-sale v1. Monthly running costs for infrastructure and developer tooling, then effort by module and the delivery workflow.

## Slide 2: One server runs the whole application
Browser
Web / mobile web
HTTPS
Azure server · B2ms Linux (2 vCPU, 8 GB RAM)
Nginx web server
Serves the Angular app, free SSL certificate, forwards API calls
.NET 10 monolith (ASP.NET Core API)
Modules: Identity · Contacts · Companies · Pipeline · Follow-up · Dashboard · AI
CQRS inside one codebase, background jobs
SQL Server Express
One database on the same server
Azure Backup
Daily server backup
Azure OpenAI
AI features, pay per use
GitHub Actions
Build and deploy
Notes: No microservices, Kafka, Docker or load balancer. Everything runs on one Azure B-series Linux server: Nginx serves the Angular build and proxies the .NET 10 API; SQL Server Express runs on the same machine.

## Slide 3: Monthly costing
Azure infrastructure, then developer tooling as a separate cost

## Slide 4: Azure infrastructure costs about $102 a month
Item | Choice | Monthly
Azure server | B2ms Linux, 2 vCPU, 8 GB RAM | $77.38
Server disk | 128 GB Standard SSD | $9.60
Static public IP | Standard, 1 address | $3.65
SQL Server | Express edition on the same server | $0.00
Backup | Azure Backup, 1 server + ~64 GB storage | $11.43
.NET 10, Angular, Nginx, SSL | Open source / free certificate | $0.00
Infrastructure total |  | $102.06
$102.06
Azure infrastructure per month
$1,224.72
Azure infrastructure per year
Domain name is costed separately. Azure list prices, Southeast Asia (Singapore), USD, Azure Retail Prices API, Oct 2026 · 730 hours/month

## Slide 5: B2ms is the right size for one server
OPTION
B2s
2 vCPU · 4 GB RAM
$38.54
per month, Linux
Too little memory for .NET, SQL Server and Nginx together
RECOMMENDED
B2ms
2 vCPU · 8 GB RAM
$77.38
per month, Linux
Recommended. Room for the API, database and web server
OPTION
B4ms
4 vCPU · 16 GB RAM
$154.03
per month, Linux
Upgrade path when customer numbers grow
Server size can be changed later in minutes, with a short restart. Azure list prices, Southeast Asia (Singapore), USD, Azure Retail Prices API, Oct 2026 · 730 hours/month

## Slide 6: SQL Server Express on the server costs nothing
Option | Limits | Monthly
SQL Server Express on the B2ms server (recommended) | 10 GB per database, uses server memory | $0.00
Azure SQL Database Basic | 5 DTU, 2 GB, managed backups | $4.90
Azure SQL Database Standard S0 | 10 DTU, 250 GB, managed backups | $14.72
When to move: if the database nears 10 GB or the server runs short of memory, move to Azure SQL S0. The application code does not change, only the connection string.
Azure list prices, Southeast Asia (Singapore), USD, Azure Retail Prices API, Oct 2026 · 730 hours/month

## Slide 7: The software stack adds no licence cost
$0
.NET 10
Runtime and SDK are free and open source; the API runs on Linux with no Windows licence
$0
Angular
Built to static files and served by Nginx on the same server; no separate hosting fee
$0
Nginx + SSL
Free web server; Let's Encrypt certificate renews automatically
$0
Bandwidth
First 100 GB of outbound data each month is free on Azure
Domain name is not included here; it is costed separately.

## Slide 8: Claude Max is a separate cost per developer
$100
per developer per month
Claude Max plan (5x usage tier), includes Claude Code for development work
Developers | Per month | Per year
1 | $100.00 | $1,200.00
2 | $200.00 | $2,400.00
3 | $300.00 | $3,600.00
4 | $400.00 | $4,800.00
5 | $500.00 | $6,000.00
Billed per developer, separately from Azure infrastructure
Source: claude.com/pricing (Max plan from $100/month), checked Oct 2026.

## Slide 9: Delivery plan
Effort by module and the workflow from start to ready-to-sell

## Slide 10: 583 hours from start to ready-to-sell
Chart: 
| Identity, Workspace & Team | Contacts | Companies | Pipeline & Deals | Follow-up (activities & tasks) | Home Dashboard | CSV export | AI features | Server setup & go-live
Backend | 34 | 51 | 13 | 27 | 26 | 11 | 5 | 57 | 8
Frontend | 22 | 47 | 16 | 35 | 32 | 9 | 3 | 23 | 0
QA | 11 | 17 | 5 | 11 | 9 | 4 | 1 | 17 | 0
Feature development
486 h
Server setup & go-live
8 h
Project management (8%)
40 h
Contingency (10%)
49 h
Total
583 h
Backend 232 · Frontend 187 · QA 75

## Slide 11: Six steps from requirements to ready-to-sell
1
Identity & Team
Sign-up, login, workspace, Admin vs Member, invites
67 h
2
Contacts & Companies
List, create, import, scan capture, enrich, dedupe, companies
149 h
3
Pipeline & Follow-up
Deals, Kanban, stages, won/lost, notes, calls, tasks, timeline
140 h
4
Dashboard & Export
New leads, pipeline value, tasks due, CSV export
33 h
5
AI features
Capture AI, email draft, assistant chatbot, prompted reports
97 h
6
Server setup & go-live
Azure server, SQL Server, Nginx, SSL, backup, deploy
8 h
Plus project management 40 h and contingency 49 h = 583 h in total.

## Slide 12: $102.06 a month for Azure and 583 hours of effort
One B2ms Azure server with SQL Server Express keeps running costs low
Claude Max is separate: $100 per developer per month
Upgrade to B4ms or Azure SQL S0 only when usage needs it
Not included: domain name, Azure OpenAI usage for AI features, taxes