## Summary
AILA CRM – Ready-to-sale v1: development effort estimate
Blue = editable input. Change hours on the Features / Server Setup tabs or the yellow cells here; everything recalculates.
Module | Backend (h) | Frontend (h) | QA (h) | Total (h)
1. Identity, Workspace & Team | 34 | 22 | 11 | 67
2. Contacts | 51 | 47 | 17 | 115
3. Companies | 13 | 16 | 5 | 34
4. Pipeline & Deals | 27 | 35 | 11 | 73
5. Follow-up (Activities & Tasks) | 26 | 32 | 9 | 67
6. Home Dashboard | 11 | 9 | 4 | 24
7. Integrations | 5 | 3 | 1 | 9
8. AI | 57 | 23 | 17 | 97
Feature development subtotal | 224 | 187 | 75 | 486
Other work |  |  |  | Total (h)
Server setup & production go-live (see Server Setup tab) |  |  |  | 8
Subtotal |  |  |  | 494
Project management & coordination (% of subtotal) | 8% |  |  | 40
Contingency / risk buffer (% of subtotal) | 10% |  |  | 49
GRAND TOTAL (hours) |  |  |  | 583
Assumptions
Architecture: one monolithic .NET 10 application (ASP.NET Core API) with an Angular front end, on one Azure server.
Database: SQL Server Express on the same server. No Kafka, Docker, Kubernetes or load balancer.
Scope: Identity & Team, Contacts, Companies, Pipeline & Deals, Follow-up, Home Dashboard, CSV export, AI features, server setup and go-live.
Hours are effort estimates per feature (backend, frontend, QA); project management 8% and contingency 10% are adjustable.
Not included in this estimate: discovery & architecture, UI/UX design, billing & go-to-market, system testing & UAT, hardening.
Also not in v1: outbound HubSpot/Brevo sync, lead brief, native mobile apps, data migration, legal text, marketing website, post-launch support.
Running costs (Azure, Claude Max) are on the Monthly Cost tab.

## Features
Module | Feature | Backend (h) | Frontend (h) | QA (h) | Total (h) | Notes
1. Identity, Workspace & Team | Sign up, login, email verification, password reset | 8 | 5 | 3 | 16 | ASP.NET Core Identity + ready templates
1. Identity, Workspace & Team | Workspace / org (multi-tenant data isolation) | 10 | 4 | 3 | 17 | EF Core global tenant filter in one database
1. Identity, Workspace & Team | Roles: Admin vs Member | 6 | 4 | 2 | 12
1. Identity, Workspace & Team | Invite teammates | 6 | 5 | 2 | 13 | Email invite, accept flow
1. Identity, Workspace & Team | Assign owners + My leads / deals / tasks filters | 4 | 4 | 1 | 9
2. Contacts | Contact list + detail (search, filter, paging) | 8 | 13 | 3 | 24
2. Contacts | Create / edit contact | 4 | 6 | 2 | 12
2. Contacts | Owner + status | 3 | 3 | 1 | 7
2. Contacts | Source tracking (import / scan / manual) | 2 | 2 | 1 | 5
2. Contacts | CSV import (column mapping, validation, background job) | 11 | 8 | 3 | 22 | Fixed column template first, flexible mapping later
2. Contacts | Scan capture (business card / PDF upload) | 11 | 8 | 3 | 22 | Business card + PDF only
2. Contacts | Enrich + classify | 6 | 4 | 2 | 12 | In-process background job
2. Contacts | Basic dedupe (detect + merge) | 6 | 3 | 2 | 11 | Detect on create / import, simple merge
3. Companies | Create / list / detail | 6 | 10 | 3 | 19
3. Companies | Link contacts (auto by email domain when possible) | 3 | 3 | 1 | 7 | Direct call on save, same database
3. Companies | Company search | 4 | 3 | 1 | 8
4. Pipeline & Deals | One default pipeline + stages | 4 | 2 | 1 | 7
4. Pipeline & Deals | Deals with value, owner, dates, contact / company | 9 | 10 | 3 | 22
4. Pipeline & Deals | Kanban board (drag and drop) | 4 | 11 | 3 | 18 | Angular CDK drag-drop
4. Pipeline & Deals | Deal list view | 2 | 6 | 1 | 9
4. Pipeline & Deals | Move stages + stage history | 5 | 3 | 2 | 10
4. Pipeline & Deals | Won / lost | 3 | 3 | 1 | 7
5. Follow-up (Activities & Tasks) | Notes | 4 | 5 | 1 | 10
5. Follow-up (Activities & Tasks) | Log call / meeting | 5 | 5 | 2 | 12
5. Follow-up (Activities & Tasks) | Tasks (due date, assignee, related record) | 8 | 9 | 3 | 20
5. Follow-up (Activities & Tasks) | My due / overdue | 3 | 4 | 1 | 8
5. Follow-up (Activities & Tasks) | Timeline on contact & deal | 6 | 9 | 2 | 17 | Direct SQL query, no separate read model
6. Home Dashboard | New leads widget | 3 | 3 | 1 | 7
6. Home Dashboard | Open pipeline value widget | 3 | 3 | 1 | 7
6. Home Dashboard | Tasks due + overdue widget | 2 | 3 | 1 | 6
6. Home Dashboard | Dashboard queries (SQL views) | 3 | 0 | 1 | 4 | Plain SQL views in the same database
7. Integrations | Reliable CSV export (contacts, companies, deals) | 5 | 3 | 1 | 9
8. AI | AI service foundation (Azure OpenAI client, prompts, usage metering) | 13 | 0 | 3 | 16
8. AI | Capture AI (extract / enrich / classify prompts + evaluation) | 13 | 3 | 4 | 20
8. AI | Follow-up email draft | 6 | 6 | 2 | 14
8. AI | CRM assistant chatbot (chat UI, record lookup tools) | 17 | 10 | 5 | 32 | Read-only record lookup
8. AI | Prompted reports via assistant | 8 | 4 | 3 | 15 | 5 predefined report prompts in v1
Total |  | 224 | 187 | 75 | 486

## Server Setup
Server setup & go-live task | Hours
Azure server (B2ms Linux), network, static IP | 1.5
SQL Server Express install and configuration | 1.5
Nginx web server + free SSL certificate | 1
Build and deploy pipeline (GitHub Actions) | 2
Azure Backup + basic monitoring alerts | 1
Production go-live + smoke test | 1
Total | 8

## Monthly Cost
Monthly running cost (USD)
Azure list prices, Southeast Asia (Singapore), Azure Retail Prices API, Oct 2026. Domain name is costed separately.
Azure infrastructure | Choice | Price basis | Monthly ($)
Azure server | B2ms Linux, 2 vCPU, 8 GB RAM | 0.106 per hour x 730 h | 77.38
Server disk | 128 GB Standard SSD (E10) | fixed monthly | 9.6
Static public IP | Standard, 1 address | 0.005 per hour x 730 h | 3.65
SQL Server | Express edition on the same server | free edition | 0
Backup | Azure Backup, 1 server + ~64 GB stored | $10 per server + $0.0224/GB | 11.4336
.NET 10, Angular, Nginx, SSL | Open source / free certificate | no licence | 0
Azure infrastructure total |  |  | 102.0636
Developer tooling (separate from Azure infrastructure)
Claude Max, price per developer per month |  |  | 100
Developers |  |  | Claude Max monthly ($)
1 |  |  | 100
2 |  |  | 200
3 |  |  | 300
4 |  |  | 400
5 |  |  | 500
Source: claude.com/pricing (Max plan from $100/month, includes Claude Code), checked Oct 2026.